## GeoTwit - Hours
Week	Date	Hours	Task
1	22.02.16	4	Conduction of various research on Scala and on the Play framework
2	01.03.16	0.5	Meeting with Mrs. Fatemi
	02.03.16	2	Writing of the specifications and the logbook
	04.03.16	2	Writing of the planning
	06.03.16	2	Writing of the planning and creation of the GitHub deposit
3	07.03.16	6	Analysis of the Twitter's API and of Twitter4J, and consequently writing of the analysis documentation
	08.03.16	0.5	Meeting with Mrs. Fatemi
	08.03.16	1	Analysis of the Twitter's API and of Twitter4J, and consequently writing of the analysis documentation
	13.03.16	1
4	15.03.16	0.5	Meeting with Mrs. Fatemi
	15.03.16	0.5	Analysis of the libraries usable for the geolocation as well as the interesting keywords for Switzerland, and production of a planning of news
	16.03.16	3
5	21.03.16	4.5	Installation and production of tests on Twitter4J
	22.03.16	0.5	Meeting with Mrs. Fatemi
	27.03.16	1.5	Production of stats in the prototype application
	28.03.16	3.5	Analysis of various Twitter's research
6	04.04.16	0.5	Finalization of the specifications
		3.5	Analysis of libraries concerning the maps
	05.04.16	0.5	Meeting with Mrs. Fatemi
	06.04.16	1	Adaptation of the map vizualisation app for the Tweets' visualization
	07.04.16	4	Implementation of a web-sockets system between the Java prototype application and the JavaScript one
	08.04.16	2
7	11.04.16	3	Display of Tweets in the JavaScript application
	12.04.16	0.5	Meeting with Mrs. Fatemi
	17.04.16	1.5	Production of the application's mock-up
8	18.04.16	3.5	Production of the application's mock-up and analysis of the already existing applications on the Internet
	24.04.16	3.5	Analysis of the percentage of Tweets which have geolocation tags with various parameters
9	25.04.16	4	Analysis and research of interesting subjects and minor modifications on prototype applications
	26.04.16	0.5	Meeting with Mrs. Fatemi
10	02.05.16	3	Modification of the mock-up, according to the 26.04 meeting
		5	Development of a new prototype application, allowing a user to draw a polygon all around a country by double-clicking on it
		1	Translation of documents
	03.05.16	0.5	Meeting with Mrs. Fatemi
11	09.05.16	4	Reading of the Play framework's documentation
12	16.05.16	3	Reading of the Play framework's documentation and production of test-applications
	16.05.16	5	Creation of the application's basics and modification of the documentation
	17.05.16	0.5	Meeting with Mrs. Fatemi
13	23.05.16	2	Importation of the project in the IntelliJ IDE
	23.05.16	6.5	Integration of the Twitter4J library in the project, development of the connection process and modification of the GUI
	23.05.16	1	Modification of the documentation
	24.05.16	0.5	Meeting with Mrs. Fatemi
14	30.05.16	8	Development of the search page's GUI
	31.05.16	1
	31.05.16	1	Translation of the analysis part of the documentation
	01.06.16	2
	02.06.16	1
	03.06.16	1.5
15	06.06.16	2	Translation of the analysis part
		0.5	Writing of the progress report's structure
		0.5	Translation of the specifications
	07.06.16	2	Creation and writing of the progress report
	11.06.16	1.5	Writing of the progress report
	12.06.16	3.5
16	13.06.16	4	Writing of the progress report
	14.06.16	1.5
	15.06.16	5
	16.06.16	5
	17.06.16	1
18	27.06.16	1	Production of the GANTT planning for the second half
	27.06.16	6	Implementation of sessions in GeoTwit and protection of pages (the user must be authenticated, etc.)
	28.06.16	7	Implementation of sessions in GeoTwit and protection of pages (the user must be authenticated, etc.)
	29.06.16	3	Writing of the documentation related to configurations, routes, sessions, flash scopes, cache and actions compositions
		5	Integration of maps in the application
		1	Writing of the documentation related to the drawing of rectangle by drag-and-dropping the cursor on the map
	30.06.16	4.5	Implementation of a web-sockets system between the Play's server and the JavaScript client
	30.06.16	0.5	Meeting with Mrs. Fatemi
	01.07.16	8	Implementation of the streaming process in GeoTwit with web sockets
19	04.07.16	4	Writing of the documentation related to JavaScript routing and web sockets
	05.07.16	2
		2	Reading and validation of user's inputs for the streaming process
		1	Grouping of the Tweets on the map
		3.5	Selection of countries on the map with the drop-down menu
	06.07.16	0.5	Meeting with Mrs. Fatemi
		5	Selection of countries on the map with the drop-down menu
		1.5	Implementation of two streaming processes at the same time, when the user filled the two keywords sets
	07.07.16	0.5	Filtering of Tweets by language
		7	Display of streaming information (number of received Tweets, speed, etc.)
	08.07.16	0.5	Analysis of the FR-DE match of the Euro2016 event
		8.5	Implementation of the streamings' charts
	09.07.16	1
		1	Handling of exceptions
	10.07.16	1	Writing of the documentation related to the analysis of the Euro 2016's final
20	11.07.16	7	Writing of the documentation related to the last week's implementation
	12.07.16	5	Reading and validation of user's inputs for the static mode
	13.07.16	0.5	Writing of the documentation related to the langages' selection
		4.5	Reading and validation of user's inputs for the static mode and retrieval of Tweets from the server
		0.5	Meeting with Mrs. Fatemi
	14.07.16	6.5	Implementation of the static mode
	15.07.16	4
		3	Generation of the backup files of the streaming's results
21	18.07.16	4	Generation of the backup files of the streaming's results
		4	Writing of the documentation related to the static mode and the generation of backup files
		1	Review of the documentation
	19.07.16	6
		2	Writing of the documentation related to the generation of the backup files
	20.07.16	0.5	Meeting with Mrs. Fatemi
		3.5	Implementation of the about and help pages and modification of the GUI
	21.07.16	8	Implementation of the files' importation.
	22.07.16	5
		1	Writing of the documentation related to the files' importation.