## Sheet1
GANTT | [7 empty] | Reports: |  |  | 1. Progress report | [7 empty] | 2. Final report
Weeks
| Task | Description | Duration [sem] | 1 | 2 | 3 | 4 | 5 | Easter holidays | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Reports | [9 empty] | 16: 1; 22: 2
Documentation |  |  | 21
| T1 | Logbook | 21
| T2 | Specifications | 4
| T3 | Planning | 1
| T4 | Repports | 19 | bar: 6 to 20
| T5 | Set-Up instructions | 1 | bar: 19
| T6 | Instruction manual | 1 | bar: 19
Analysis |  |  | 4
| T7 | Adoption of the Twitter's APIs | 2 | bar: 6
| T8 | Installation of the basic components | 1 | bar: 8
| T9 | Analysis of Scala and of Play Framework | 2 | bar: 6; 8
| T10 | UML schema of the application | 1 | bar: 8
| T11 | Mock-Up | 1 | bar: 7
Conception of the basic functionalities |  |  | 5 | bar: 9 to 13
| T12 | Tweets retrieval | 1 | bar: 9
| T13 | Collected Tweets' analysis | 2 | bar: 9 to 10
| T14 | Basic Development | 4
| T14-1 | Search of Tweets by keywords | 2 | bar: 11 to 12
| T14-2 | Visualization of the Tweets without a map | 3 | bar: 11 to 13
| T14-3 | GUI | 4 | bar: 10 to 13
Conception of the advanced functionalities |  |  | 8 | bar: 14 to 20
| T15 | Advanced development | 5
| T15-1 | Filtering of the search by geographic areas | 1 | bar: 14
| T15-2 | Visualization of the results on a map | 3 | bar: 15 to 16
| T15-3 | Interaction with the map | 3 | bar: 16 to 17
| T15-4 | GUI | 5 | bar: 14 to 17
| T16 | Development of a grouping algorithm | 3 | bar: 17 to 19
| T17 | Miscellaneous (help, « about » page, etc.) | 1 | bar: 20
Tests et validation |  |  | 15 | bar: 6 to 20
| T18 | Functional Tests | 11 | bar: 8 to 18
| T19 | Final Tests | 2 | bar: 19 to 20
Time frame (in case of delay) |  |  | 2 | bar: 21 to 22