## Feuille1
Week	Date	Hours	Task
1	22.02.16	4	Various research on Scala as well as on the Play framework.
2	01.03.16	0.5	Meeting with Mrs. Fatemi.
	02.03.16	2	Writing of the specifications and the logbook.
	04.03.16	2	Writing of the planning.
	06.03.16	2	Writing of the planning and creation of the GitHub deposit.
3	07.03.16	6	Analysis of the Twitter's API and of Twitter4J, and consequently writing of the analysis documentation.
	08.03.16	0.5	Meeting with Mrs. Fatemi.
	08.03.16	1	Analysis of the Twitter's API and of Twitter4J, and consequently writing of the analysis documentation.
	13.03.16	1
4	15.03.16	0.5	Meeting with Mrs. Fatemi.
	15.03.16	0.5	Analysis of the libraries usable for the geolocation as well as the interesting keywords for Switzerland, and production of a news planning.
	16.03.16	3
5	21.03.16	4.5	Installation and production of tests on Twitter4J.
	22.03.16	0.5	Meeting with Mrs. Fatemi.
	27.03.16	1.5	Production of stats in the test-app.
	28.03.16	2	Analysis of various Twitter's research.
		1.5	Update documentation.
6	04.04.16	0.5	Finalization of the specifications.
		3.5	Tâchewith maps' libraries.
	05.04.16	0.5	Meeting with Mrs. Fatemi.
	06.04.16	1	Adaptation of the map vizualisation app for the Tweets vizualisation.
	07.04.16	4	Implementation of a Websockets system between the Java application and the JavaScript one.
	08.04.16	2
7	11.04.16	3	Display of Tweets on the JavaScript application.
	12.04.16	0.5	Meeting with Mrs. Fatemi.
	17.04.16	1.5	Production of the application's mockup.
8	18.04.16	3.5	Production of the application's mockup and analysis of the existing.
	24.04.16	3.5	Analysis of the percentage of Tweets which own geolocation tags with various parameters.
9	25.04.16	4	Analysis and research of interesting subjects and minor updates on test applications.
	26.04.16	0.5	Meeting with Mrs. Fatemi.
10	02.05.16	3	Update mockup, according to the 26.04 metting.
		5	Develop a new test-app, which allows an user to draw a polygon all around a country by double-clicking on it.
		1	Translate documents.
	03.05.16	0.5	Meeting with Mrs. Fatemi.
11	09.05.16	4	Reading of the Play Framework's documentation.
12	16.05.16	3	Reading of the Play Framework's documentation and production of test-applications.
	16.05.16	5	Creation of the application's basics and update documentation.
	17.05.16	0.5	Meeting with Mrs. Fatemi.
13	23.05.16	2	Importation of the project in the IntelliJ IDE.
	23.05.16	6.5	Integration of the Twitter4J library in the project, develpoment of the connection process and modification of the GUI.
	23.05.16	1	Update documentation.
	24.05.16	0.5	Meeting with Mrs. Fatemi.
14	30.05.16	8	Development of the search-page's GUI.
	31.05.16	1	Development of the search-page's GUI.
	31.05.16	1	Translation of the analysis part of the documentation.
	01.06.16	2
	02.06.16	1
	03.06.16	1.5
15	06.06.16	2	Translation of the analysis part.
		0.5	Writing of the progress report's structure.
		0.5	Translation of the specifications.
	07.06.16	2	Creation and writing of the progress report.
	11.06.16	1.5	Writing of the progress report.
	12.06.16	3.5	Writing of the progress report.
16	13.06.16	4	Writing of the progress report.
	14.06.16	1.5	Writing of the progress report.
	15.06.16	5	Writing of the progress report.
	16.06.16	5	Writing of the progress report.
	17.06.16	1	Writing of the progress report.
TOTAL		134