## Sheet1
GeoTwit – GANTT Planning of the Second Half |  |  |  | Reports: |  | 2. Final report
Weeks
| Task | Description | Duration [weeks] | 18 | 19 | 20 | 21 | 22
2
Documentation |  |  | 5
| T1 | Logbook | 5
| T2 | Planning | 1
| T3 | Reports | 5
| T4 | Set-Up instructions | 1
| T5 | Instruction manual | 1
Development of the application |  |  | 4
| T6 | Protection of the pages (user must be connected, etc.) | 1
| T7 | Integration of maps in the app | 1
| T8 | Validation of the search forms | 1
| T9 | Implementation of the Streaming process in the app | 2
| T9-1 | Search and display of grouped Tweets on the map | 2
| T9-2 | Implementation of charts | 1
| T10 | Implementation of the static mode | 2
| T10-1 | Display of grouped Tweets on the map | 1
| T10-2 | Accelerated streaming mode | 2
| T11 | Development and integration of a pop-up tutorial | 2
| T12 | Pages | 1
| T12-1 | Finalization of the Home Page | 1
| T12-2 | Help Page | 1
| T12-3 | About Page | 1
| T13 | Finalization of the application | 1
Tests et validation |  |  | 4
| T14 | Functional Tests | 3
| T15 | Final Tests | 1
| T16 | Analysis of interesting subjects with the application | 2